## NestJS Plan
Phase | Phase Name | Task / Module | รายละเอียด | วันทำงาน | วันเริ่ม | วันสิ้นสุด | หมายเหตุ
Phase 1 | Foundation & Auth
Phase 1 | Foundation & Auth | Project Setup | NestJS init, TypeORM/Prisma, PostgreSQL, .env, CORS, Swagger | 1 | 21/04/2569 | 21/04/2569
Phase 1 | Foundation & Auth | Auth Module | JWT login/refresh, bcrypt, Guards, @CurrentUser decorator | 1 | 22/04/2569 | 22/04/2569
Phase 1 | Foundation & Auth | Users Module | CRUD accounts, roles (admin/hr/user), password reset | 1 | 23/04/2569 | 23/04/2569
Phase 2 | Master Data
Phase 2 | Master Data | Organization | Division → Department → Section → Line → JobLevel CRUD | 1 | 24/04/2569 | 24/04/2569
Phase 2 | Master Data | Employees | CRUD + filters (division/dept/section/level/route/status) + QR data | 1 | 27/04/2569 | 27/04/2569
Phase 2 | Master Data | Drivers | CRUD, vehicle assignment, license info | 1 | 28/04/2569 | 28/04/2569
Phase 2 | Master Data | Vendors | CRUD, contact info | 1 | 29/04/2569 | 29/04/2569
Phase 2 | Master Data | Vehicles + VehicleTypes | CRUD, type management, status, capacity, insurance | 1 | 30/04/2569 | 30/04/2569
Phase 3 | Route & Schedule
Phase 3 | Route & Schedule | Routes + Trips + Points | Route → Trip → Point hierarchy, coordinates, order | 2 | 01/05/2569 | 04/05/2569
Phase 3 | Route & Schedule | Shifts | day/night toggle, time range, CRUD | 1 | 05/05/2569 | 05/05/2569
Phase 3 | Route & Schedule | Posts | เชื่อม Route + Shift + Driver + Vehicle + Vendor | 1 | 06/05/2569 | 06/05/2569
Phase 3 | Route & Schedule | Booking Policies | Rules per company/mode, advance booking limits | 1 | 07/05/2569 | 07/05/2569
Phase 4 | Core Business
Phase 4 | Core Business | Reserves / Bookings | State machine (waiting→approved→finished/canceled), bulk approve, date/shift filters | 2 | 08/05/2569 | 11/05/2569
Phase 4 | Core Business | Attendances | RFID/QR scan, validate reserve, duplicate check, date range filters | 2 | 12/05/2569 | 13/05/2569
Phase 5 | Communication
Phase 5 | Communication | Notifications | once/daily/daily_until scheduling, broadcast, read status | 1 | 14/05/2569 | 14/05/2569
Phase 5 | Communication | Feedback | Inbox pattern, admin reply, status workflow (open/investigating/resolved/closed) | 1 | 15/05/2569 | 15/05/2569
Phase 6 | Reports & Dashboard
Phase 6 | Reports & Dashboard | Dashboard KPIs | Active employees, bookings, boarding rate, no-shows, vehicle/route counts | 1 | 18/05/2569 | 18/05/2569
Phase 6 | Reports & Dashboard | Auth Logs | Login/logout events, IP, device, result (success/fail) | 1 | 19/05/2569 | 19/05/2569
Phase 6 | Reports & Dashboard | Report: Attendance | Aggregate by date/type/status, export | 1 | 20/05/2569 | 20/05/2569
Phase 6 | Reports & Dashboard | Report: Vehicles | Per-vehicle stats (driver, vendor, posts, scans, routes served) | 1 | 21/05/2569 | 21/05/2569
Phase 6 | Reports & Dashboard | Report: Usage | Daily trend aggregation, boarding rate over time | 1 | 22/05/2569 | 22/05/2569
Phase 7 | Advanced Features
Phase 7 | Advanced Features | Settings / Modules | Module toggle, RFID timeout, reserve limits, language config | 1 | 25/05/2569 | 25/05/2569
Phase 7 | Advanced Features | Calendar / Holidays | Holiday CRUD, workday marking, recurring patterns | 1 | 26/05/2569 | 26/05/2569
Phase 7 | Advanced Features | Route Optimization API | VRP solver (รับ reserves → คืน vehicle assignments), OR-Tools style | 2 | 27/05/2569 | 28/05/2569
|  | รวมทั้งหมด |  | 28 | 21/04/2569 | 28/05/2569

## Gantt
Phase | Task / Module | Hours | Start | End | W1 20/04 | W2 27/04 | W3 04/05 | W4 11/05 | W5 18/05 | W6 25/05 | W7 01/06
Phase 1 | Project Setup | 4 | 21/04/2569 | 21/04/2569 | █
Phase 1 | Auth Module | 8 | 22/04/2569 | 22/04/2569 | █
Phase 1 | Users Module | 4 | 23/04/2569 | 23/04/2569 | █
Phase 2 | Organization | 6 | 24/04/2569 | 24/04/2569 | █
Phase 2 | Employees | 6 | 27/04/2569 | 27/04/2569 | █
Phase 2 | Drivers | 4 | 28/04/2569 | 28/04/2569 |  | █
Phase 2 | Vendors | 3 | 29/04/2569 | 29/04/2569 |  | █
Phase 2 | Vehicles + VehicleTypes | 6 | 30/04/2569 | 30/04/2569 |  | █
Phase 3 | Routes + Trips + Points | 8 | 01/05/2569 | 04/05/2569 |  | █
Phase 3 | Shifts | 4 | 05/05/2569 | 05/05/2569 |  |  | █
Phase 3 | Posts | 6 | 06/05/2569 | 06/05/2569 |  |  | █
Phase 3 | Booking Policies | 4 | 07/05/2569 | 07/05/2569 |  |  | █
Phase 4 | Reserves / Bookings | 10 | 08/05/2569 | 11/05/2569 |  |  | █
Phase 4 | Attendances | 10 | 12/05/2569 | 13/05/2569 |  |  |  | █
Phase 5 | Notifications | 5 | 14/05/2569 | 14/05/2569 |  |  |  | █
Phase 5 | Feedback | 5 | 15/05/2569 | 15/05/2569 |  |  |  | █
Phase 6 | Dashboard KPIs | 6 | 18/05/2569 | 18/05/2569 |  |  |  | █
Phase 6 | Auth Logs | 4 | 19/05/2569 | 19/05/2569 |  |  |  |  | █
Phase 6 | Report: Attendance | 4 | 20/05/2569 | 20/05/2569 |  |  |  |  | █
Phase 6 | Report: Vehicles | 4 | 21/05/2569 | 21/05/2569 |  |  |  |  | █
Phase 6 | Report: Usage | 4 | 22/05/2569 | 22/05/2569 |  |  |  |  | █
Phase 7 | Settings / Modules | 4 | 25/05/2569 | 25/05/2569 |  |  |  |  | █
Phase 7 | Calendar / Holidays | 5 | 26/05/2569 | 26/05/2569 | [5 empty] | █
Phase 7 | Route Optimization API | 12 | 27/05/2569 | 28/05/2569 | [5 empty] | █